## Pre-app
NSIPs and large-scale energy projects progress
Last update 02/10/2025
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
ESW RTS | Water pipeline and reservoir | North Mid Suffolk from Metfield / Laxfield to Eye | DC/25/02839 | Pre-app | Non-statutory consultation expected 29th Oct-10th Dec. Scoping Q2 26. | https://www.nwg.co.uk/globalassets/wrmp/nwg/october-24/esw/esw-wrmp24-main-report_final-oct-24.pdf
ESW WSR | Water pipeline and reservoir | Site TBC. Possibly affecting Metfield | DC/25/04128 | Pre-app | Pre-consultation site survey and selection work underway | https://www.nwg.co.uk/globalassets/wrmp/nwg/october-24/esw/esw-wrmp24-main-report_final-oct-24.pdf
Copdock interchange | NSIP:Highway works | Copdock / Belstead | DC/21/06027 | Pre-app | Options consultation report published 25th March 2022. Awaiting further update from DfT and publication of RIS3 /4 | https://nationalhighways.co.uk/our-work/pipeline-of-possible-future-schemes/a14-junction-55-copdock-interchange/
White Elm solar farm | NSIP: Solar farm | Mendlesham / Thwaite / Wickham Skieth | DC/24/00377 | Pre-app | Project paused indefinitely. Informal consultation cancelled. | www.whiteelmsolarfarm.com
EcoPower Suffolk | NSIP: Solar and BESS | Stuston / Occold / Thrandeston / Yaxley | DC/24/02748 | Pre-app | Scoping expected Autumn / winter 25. Statutory consultation expected Summer 26. Submission expected 2027 | https://ecopowersuffolk.com/
Tarchon | Interconnector | Ardleigh | DC/25/01361 | Pre-app | Formal consultation expected 2025/26 | https://www.tarchonenergy.net/
Green Switch Capital | Solar farm | Bentley | DC/22/04255 and DC/22/03371 | EIA Screening and pre-app | Screening opinion published Aug 22. Application submitted. | https://gscapital.co.uk
WP Grid Services | Grid stability infrastructure | Bramford | DC/21/06759 | EIA Screening | Screening opinion published Dec 2021. | https://www.welshpower.com/index.html
Aura Power | Solar farm | Palgrave | DC/22/02592, DC/22/05600 and DC/23/02362 | Pre-app, EIA screening and EIA scoping | Pre-app enquiry completed. EIA screening opinion published. EIA scoping issued. Application submitted. | https://www.aurapower.com/
RNA Energy | Solar farm | Burstall and Hintlesham | DC/22/03498 | Pre-app | Pre-app enquiry completed. | https://www.rna-energy.com/
Pegasus group | Solar farm | Boxted | DC/22/04456 and DC/22/06236 | Pre-app and EIA screening | Pre-app enquiry completed. Application submitted. | https://www.pegasusgroup.co.uk/
DLP consultants | Solar farm | Earl Stonham | DC/22/05886, DC/23/01385 and DC/23/04644 | Pre-app, EIA screening and application | Pre-app enquiry completed. Application submitted. | www.dlpconsultants.co.uk
LGT | Solar farm | Brent Eleigh, Lavenham | DC/23/00974 | Pre-app | Pre-app enquiry completed. | https://www.lgtwm.com/uk-en/
The Marquis PH | Solar farm | Layham | DC/23/01435 | Pre-app | Pre-app enquiry completed. | N/A
Clearstone Energy | BESS | Bramford | DC/23/01845 and DC/24/02300 | Pre-app and EIA screening | Pre-app enquiry completed. Screening opinion published. Application submitted | https://www.clearstoneenergy.com/
Amp Clean Energy | Hydrogen | Stowmarket | DC/23/03960 | Pre-app | Pre-app enquiry completed. | https://www.ampcleanenergy.com/
Industria Brand Energy Group | Solar farm | Combs | DC/24/00615 | Pre-app | Pre-app enquiry completed. | https://regener8power.com/
Octopus | Wind turbine | Stradbroke | DC/24/02865 | Pre-app | Pre-app enquiry completed. | https://octopusenergy.com/
Cranswick | Wind turbine | Eye | DC/24/03890 and DC/24/03997 | Pre-app and EIA screening | Pre-app enquiry completed.
Field Yaxley | BESS | Yaxley / Eye | DC/24/05186 | Pre-app | Pre-app enquiry completed. Application submitted. | https://www.fieldyaxley.co.uk/
TBC | Solar Farm | Akenham | DC/24/05387 | Pre-app | Pre-app enquiry completed
Regener8 | BESS | Yaxley | DC/25/01051 and DC/24/04302 | Pre-app and EIA screening | Pre-app advice issued. Screening opinion published | https://regener8power.com/
DWD Lts | BESS | Bramford and Burstall | DC/25/00975 | Pre-app | Pre-app advice issued. | dwd-ltd.co.uk
Regener8 | Solar farm | Botesdale | DC/25/00998 and DC/25/02254 | Pre-app and EIA screening | Pre-app advice issued. Screening opinion published. Application submitted. | https://regener8power.com/
OPDE UK Ltd | Solar farm | Hessett | DC/24/05579 and DC/25/01157 | Pre-app and EIA Screening | Pre-app advised issued. Screening opinion published | https://opdenergy.com/en/
Ethos Green Energy | BESS | Hadleigh | DC/25/02286 | Pre-app | Pre-app advice issued | https://ethosgreenenergy.com/
Ethos Green Energy | BESS | Burstall | DC/25/02289 | Pre-app | Pre-app advice issued | https://ethosgreenenergy.com/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused

## Live apps
NSIPs and large-scale energy projects progress
Last update 02/10/2025
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
Norwich to Tilbury | NSIP: Overhead lines | Norfolk-Suffolk-Essex | DC/21/05611 | Examination | Accepted for examination - expected to start Dec/Jan. Ongoing meetings. | https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/norwich-to-tilbury
5 Estuaries | NSIP: Offshore wind farm | Offshore and Essex (grid connection to be shared with Norwich to Tilbury) | DC/21/05734 | Examination | Awaiting SoS decision | https://fiveestuaries.co.uk/
North Falls | NSIP: Offshore wind farm | Offshore and Essex (grid connection to be shared with Norwich to Tilbury) | DC/21/04710 | Examination | Awaiting SoS decision | https://www.northfallsoffshore.com/
SEA Link | Sub-sea cable | Mostly offshore from East Suffolk District | DC/22/05326 | Examination | Examination in progress | https://www.nationalgrid.com/the-great-grid-upgrade/sea-link
Pegasus group | Solar farm | Boxted | DC/23/05127 | Application pending determination | Awaiting consultee advice. Officer prepaing report for Committee | https://www.pegasusgroup.co.uk/
Connectid 2 Ltd | Solar farm | Botesdale | DC/25/03257 | Application pending determination | Officer preparing report for Committee | https://regener8power.com/
OPDE | Solar farm | Hesset | DC/25/02730 | Application pending determination | Officer preparing report for Committee | https://opdenergy.com/en/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused

## Determined
NSIPs and large-scale energy projects progress
Last update 02/10/2025
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
EA1 | Sub station for underground cable from offshore wind farm | Bramford | 0116/14 and 2315/11 | Operational. | Completed and operational. Ongoing monitoring and meetings. | https://www.scottishpowerrenewables.com/pages/east_anglia_one.aspx
EA3 | Converter station for underground cables from offshore wind farm | Bramford | 3490/12 | Under construction | Under construction. Additional out of hours working approved. Ongoing meetings. | https://www.scottishpowerrenewables.com/pages/east_anglia_three_background.aspx
Progress Power | Gas-fired power station | Eye | DC/21/03894 | Under construction. | Under construction. Additional out of hours working approved. Preparing for commissioning. Ongoing meetings. | https://www.drax.com/about-us/our-projects/progress-power/
Sizewell C | Nuclear power station | Sizewell | DC/21/02517 | Under construction. | Ongoing discussion about B1078 road safety improvements. | https://www.sizewellc.com/
RNA Energy | Solar farm | Rickinghall | DC/21/06825 | Appeal determined | Refused at Committee 3rd August 2022. Appeal determined, permission granted | https://www.rna-energy.com/
ENSO (now Verdant) | Solar farm | Burstall / Flowton / Somersham | DC/20/05895 and DC/21/00060 | Applications determined | Babergh Granted, Mid Suffolk Refused - appeal allowed (permission granted).
ENSO (now Verdant) | Solar farm | Bramford / Burstall | DC/23/02118 | Application determined | Granted
Conrad Energy | Synchronous condenser | Yaxley | DC/22/04021 | Application determined | Granted | https://conradenergy.co.uk/
Conrad Energy | Synchronous condenser | Yaxley | DC/23/01494 | Under construction. | Granted. Under construction. | https://conradenergy.co.uk/
Anglian Water strategic pipeline | Water pipeline | Bury St Edmunds to Ipswich to Colchester | DC/22/06352 and DC/22/06309 | Under construction. | Granted. Under construction. Reserved matters applications expected 2025 | https://www.anglianwater.co.uk/about-us/our-strategies-and-plans/new-water-pipelines/bury-st-edmunds-to-colchester/
PACE | Solar Farm | Palgrave | DC/22/02667 | Application determined | Granted | http://www.pathfinderce.com/
Elgin Energy | Solar farm | Badley | DC/22/01530 | Application determined | Refused. Appeal allowed. Developer preparing discharge of conditions. | https://www.elgin-energy.com/
EDF | Solar farm | Bramford | DC/21/04711 | Application determined | Granted. Under construction. | https://www.edf-re.uk/our-sites/tye-lane
Statkraft | Solar Farm | Burstall / Flowton / Somersham | DC/22/00683 and DC/22/01243 | Applications withdrawn | Withdrawn by applicant | https://www.statkraft.co.uk/about-statkraft-uk/where-we-operate/Locations/greybarnsolar/
Bramford to Twinstead | NSIP: Overhead / underground power lines | Bramford to Twinstead | DC/21/01605 | Consented 12/9/24 | Under construction. Ongoing discharge of requirement submissions. Ongoing engagement regarding delivery. | https://bramford-twinstead.nationalgrid.com/consultation/our-proposals/ and https://infrastructure.planninginspectorate.gov.uk/projects/eastern/bramford-to-twinstead/
Grove Farm Solar | Solar farm | Bentley | DC/23/05656 | Application pending determination | Refused. Awaiting possible appeal
Clearstone | BESS | Bramford | DC/24/05090 | Application determined | Granted. | https://www.clearstoneenergy.com/project/bramford/
Field Yaxley | BESS | Yaxley / Eye | DC/24/05535 | Application determined | Granted. | https://www.fieldyaxley.co.uk/
Low Carbon Solar Park 27 Ltd | Solar Farm | Earl Stonham | DC/23/04644 | Application determined | Granted. | https://www.lowcarbon.com/
Aura Power | Solar farm | Palgrave | DC/23/05426 | Application determined | Granted. | https://www.aurapower.com/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused